## issues
ID | Work Item Type | Title | Description | Assigned To | Priority | State | Tags
4 | Issue | ATM asks for PIN when an invalid card is inserted | ATM asks for PIN even when an invalid card is inserted into ATM. Function being tested:&nbsp;Session Initial state of the system:&nbsp; ATM is off. Steps to reproduce: 1. Turn on the ATM and enter a valid number of bills. 2. Insert an invalid card. Expected outcome: A Failure Message saying &quot;Invalid Card&quot; as soon as the card is inserted. Actual outcome: The ATM asks the user to enter the PIN. Displays the invalid card message after the PIN is entered. Regression Test Defect still exists in version 1.1 | Abhilash Paul | 3 | Doing | v1.0; v1.1
5 | Issue | When performing balance enquiry for the Money Market account on card 2, Invalid Account Type message is shown although it is a valid account. | When performing a balance enquiry for the Money Market account on card 2, the ATM shows 'Invalid Account Type' error message even though it is a valid account. Function being tested: Balance Inquiry Initial State of the system:&nbsp;The ATM is off. Steps to reproduce: 1. Turn on the ATM and&nbsp;insert a valid number of bills 2. Insert card 2 3. Enter the PIN as 1234&nbsp; 4. Choose Balance Inquiry 5. Choose Money Market Expected Outcome ATM displays a receipt showing the balance of the Money Market account. Actual Outcome ATM displays an invalid account type message. | Abhilash Paul | 2 | Done | v1.0; v1.1
6 | Issue | ATM shows Savings account option when performing withdrawal operation using card 2 | Card number 2 has only two accounts associated with it: Checking and Money Market Note. When trying to make a withdrawal, the ATM shows the Savings account as an option Function being tested:&nbsp;Withdrawal Initial state of the system:&nbsp; ATM is off. Steps to reproduce: 1. Turn on the ATM and enter a valid number of bills. 2. Insert card number 2 and enter the PIN 3. Choose withdrawal Expected outcome: The ATM lists Checking and Money Market accounts as accounts to withdraw from Actual outcome: The ATM lists Checking, Money Market and Savings&nbsp;as accounts to withdraw from. | Abhilash Paul | 2 | Doing | v1.0
7 | Issue | ATM dispenses $60 when $40 is withdrawn from money market account using card 2 | When requested withdrawal of $40 from the Money Market account using card number 2, the ATM dispensed $60 instead. Function being tested:&nbsp;Withdrawal Initial state of the system:&nbsp; ATM is off. Steps to reproduce: 1. Turn on the ATM2. Enter a number greater than or equal to 4 for the number of $20 bills. 3. Insert card number 2 and enter the PIN 4. Choose withdrawal5. Choose the Money Market account6. Choose $40 Expected outcome: The ATM dispenses the requested amount of $40 Actual outcome: The ATM dispenses $60 | Abhilash Paul | 2 | Done | v1.0
8 | Issue | ATM dispenses $20 when trying to withdraw $200 from checking account using card 2 | When requested a withdrawal of $200 from the Checking account with a current balance of $100, the ATM dispensed $20 instead of showing a message that said 'insufficient fund'. Checking account&nbsp; Function being tested:&nbsp;Withdrawal Initial state of the system:&nbsp; ATM is off. Steps to reproduce: 1. Turn on the ATM and enter a valid number of bills. 2. Insert card number 2 and enter the PIN 3. Choose withdrawal4. Choose the Checking account5. Choose $200 Expected outcome: No cash is dispensed. Instead, the ATM should show a message informing the user that there is not sufficient to perform requested withdrawal. Actual outcome: The ATM dispenses $20 | Abhilash Paul | 2 | Done | MFT; v1.0; v1.1
9 | Issue | ATM does not dispense $20 even though it has $20 in the cash dispenser. | The ATM does not dispense when the requested withdrawal amount is exactly same as the cash it has in the dispenser. Instead, it shows the error message that says 'Insufficient cash available'.&nbsp; Function being tested:&nbsp;Withdrawal Initial state of the system:&nbsp; ATM is off. Steps to reproduce: 1. Turn on the ATM 2. Enter '1' for the number of $20 bills. 2. Insert card number 2 and enter the PIN 3. Choose withdrawal4. Choose the Checking account5. Choose $20 Expected outcome: The ATM dispenses $20 Actual outcome: No cash is dispensed. Instead, the ATM should show&nbsp;the error message that says 'Insufficient cash available'. | Abhilash Paul | 2 | Done | v1.0; v1.1
10 | Issue | Wrong balance showing after depositing to checking account | When $20 deposited to the checking account, the total balance changed from $60 to $70. Function being tested:&nbsp;Deposit Initial state of the system:&nbsp; ATM is on and waiting for the user to insert the amount to be deposited. Steps to reproduce: 1. Turn on the ATM and do a balance enquiry. 2. Select the deposit option and enter $20 and check the balance in the receipt again. Expected outcome: The ATM shows the correct amount of balance. Actual outcome: The ATM shows $10 less as balance. Regression testing: The defect still exists in version 1.1. The balance shown is $119.9 instead of the expected $120. | Neha Tom Merin | 2 | Doing | v1.0; v1.1
11 | Issue | Wrong card number displaying in the receipt | For card 1, the ATM displays card 2 and for card 2, the ATM displays card 3 in the receipt. Function being tested:&nbsp;Session Initial state of the system:&nbsp; ATM is on and waiting for the user to do a transaction. Steps to reproduce: 1. Turn on the ATM and enter the card number. 2. Do a transaction and check the transaction history displayed. Expected outcome: Correct Card number showed for each card Actual outcome: card 1 displays as card 2 and card 2 displayed as card 3. Regression testing: The defect still exists in version 1.1 | Neha Tom Merin | 2 | Doing | v1.0; v1.1
12 | Issue | ATM shows Money Market account instead of savings account for card 1 | Card 1 is supposed to have checking account and savings account. But, the ATM shows Money Market instead of savings. Function being tested:&nbsp;Balance enquiry Initial state of the system:&nbsp; ATM is off. Steps to reproduce: Turn on the ATM and enter a valid number of bills. Click on insert card Insert 1 and press enter enter the PIN 42 selected option 4 balance inquiry Expected outcome: ATM should display the available accounts, which are checking and savings Actual outcome: The ATM displays money market account instead of savings. Regression testing: The defect still exists in version 1.1. The ATM displays money market account along with checking and savings. | Neha Tom Merin | 2 | Doing | v1.0; v1.1
13 | Issue | Invalid Account type while depositing money to Money Market | Function being tested:&nbsp;Depsoits Initial state of the system:&nbsp; ATM is ON and waiting for the user to insert the card. Steps to reproduce: Insert card 1 type correct PIN 42 and press enter select option 2 for deposits select option 3 for money markets typed $100 and press entered Expected outcome: Should have asked to insert bills into ATM machine Actual outcome:A failure message saying &quot;Invalid Account Type&quot;&nbsp; Regression Test:Defect still exists in version 1.1 | Bilal Ahmed | 2 | Doing | v1.0; v1.1
14 | Issue | Less money transferred between accounts, than entered, for card 1 | Entered $100 to transfer from one account to another, but only $99.50 got transferred. Function being tested:&nbsp;Transfer Initial state of the system:&nbsp; ATM is on and waiting for the user to enter an amount that needs to be transferred. Steps to reproduce: 1. Turn on the ATM and insert card 1 and do a transfer from savings to checking. 2. Enter an amount and check the receipt. Expected outcome: ATM transfers the exact amount of money asked. Actual outcome: The ATM transfers $0.50 less. | Neha Tom Merin | 2 | Done | v1.0
15 | Issue | Transfer receipt shows the inverted 'from' and 'to' account names for card 1 | The receipt shows wrong account names after a transfer. If a transfer made from checking to savings, the receipt shows 'from: savings to: checking' and vice versa.Function being tested:&nbsp;Transfer Initial state of the system:&nbsp; ATM is on and waiting for the user to enter the transfer amount. Steps to reproduce: 1. Turn on the ATM and insert card 1. 2. Select Balance transfer from any account to another and enter an amount. 3. Check the receipt for the 'from and to' information. Expected outcome: Receipt showing the correct 'from and to' account names. Actual outcome: Receipt shows the wrong account names. | Neha Tom Merin | 2 | Doing | v1.0
16 | Issue | Entered card 3 along with PIN and system hanged | Function being tested: Error Handling Initial state of the system:&nbsp; ATM is ON and waiting for the user to insert the card. Steps to reproduce: Insert card 3 type PIN 1234 and press enter Expected outcome: Should have issued error invalid card/pin but the ATM asked for PIN Actual outcome:System hanged after inserting the PIN and now I can't turn off the ATM, cancel button is also not working. Force shut down was required. | Bilal Ahmed | 2 | Done | v1.0; v1.1
18 | Issue | ATM shows unknown error while enquiring about balance on card 1 from Money Market account | Card 1 has only two accounts associated with it: Checking and Savings. When trying to make a balance inquiry, the ATM shows the Money Market account as an option 2 and savings account was missing all together. Press option 2 to see the system behavior Function being tested:&nbsp;Balance Inquiry on card 1 Initial state of the system:&nbsp; ATM is off. Steps to reproduce: Turn on the ATM and enter a valid number of bills. Click on insert card Insert 1 and press enter enter the PIN 42 selected option 4 balance inquiry press option 2 money market Expected outcome: System should not proceed since card one only has checking and saving account. Actual outcome: Inital: System initally through Unknown Error and $500 popped up on the screenFinal: After few seconds ATM show receipt for savings account with $1000 balance, however card number was card 2 which is wrong card. | Bilal Ahmed | 2 | Doing | v1.0; v1.1
19 | Issue | ATM asked to re-enter correct PIN twice after wrong PIN attempt | Function being tested: Wrong Pin Test Initial state of the system:&nbsp; ATM is off. Steps to reproduce: Turn on the ATM and enter a valid number of bills. Click on insert card type 2 and press enter enter the wrong PIN 1122 Expected outcome: System should accept right PIN one time only Actual outcome: System asked to enter right PIN twiceupon entering the correct PIN 1234 and press enter, displace change below messages pop upPlease enter the PINThen press ENTERAgain entered the correct PIN 1234 and press enter, now system enter the account | Bilal Ahmed | 2 | Doing | v1.0
20 | Issue | No Limit on deposits | Function being tested: Deposit limit test Initial state of the system:&nbsp; ATM is off. Steps to reproduce: Turn on the ATM and enter a valid number of bills. Click on insert card type 2 and press enter type correct PIN 1234 option 2 selected to deposit option 1 selected for checking account entered 99999999999999.99 and press enter then system hanged up Expected outcome: There should be some minimum and maximum limit on deposit Actual outcome:System hanged up, was not able to cancel or turn OFF the ATTM, eventually ATM was forced shut down and restart again. | Bilal Ahmed | 2 | Doing | v1.0
21 | Issue | Issue with Balance Calculation After Withdrawal from Checking | I initially deposited $55.55 into the checking account, which updated the total balance to $3035.55. The available balance was displayed as $1000. Later, in the same operation, we withdrew $20 from the checking account. However, instead of deducting the withdrawal amount from the total balance ($3035.55), the system incorrectly updated both the total and available balances to $80. Steps to Reproduce: 1.&nbsp;Deposit $55.55 into the checking account. 2.&nbsp;The total balance should update to $3035.55, and the available balance should show $1000. 3.&nbsp;Withdraw $20 from the checking account. 4.&nbsp;Observe the updated total and available balances. Expected Behavior: After the $20 withdrawal, the total balance should be updated to $3015.55 (total balance of $3035.55 minus the $20 withdrawal). The available balance should also adjust accordingly. Actual Behavior: The total and available balance both incorrectly update to $80 after the withdrawal. | Jasmeen Kaur | 2 | Done | v1.0; v1.1
22 | Issue | Dispensed: $20.00 log appeared everytime on each wrong selection from menu | Function being tested: Wrong selection from main menu Initial state of the system:&nbsp; ATM is off. Steps to reproduce: Turn on the ATM and enter a valid number of bills. Click on insert card type 2 and press enter type PIN 1234 and press enter select any option other then 1,2,3 and 4 Expected outcome: No changes should happen to system Actual outcome:System hanged up for few seconds on each wrong selection button press, and every time a log appear in log history &quot;Dispensed: $20.00&quot;.In below picture number 9 and 5 were pressed&nbsp; Log history was checked after wrong selection Regression test The defect still exists in version 1.1 when option 5 is chosen. All other options are working as expected. | Bilal Ahmed | 2 | Doing | v1.0; v1.1
23 | Issue | No Limit on PIN value | Function being tested: PIN max limit test Initial state of the system:&nbsp; ATM is off. Steps to reproduce: Turn on the ATM and enter a valid number of bills. Click on insert card type 2 and press enter type PIN 99999999999999999999999 and press enter Expected outcome: ATM should limit maximum and minimum PIN Actual outcome:&nbsp;ATM hanged, neither cancel was working nor ATM OFF and ATM was forced shut down. | Bilal Ahmed | 2 | Doing | v1.0
24 | Issue | System does not accept number of $20 bills greater than 2147483647 | MFT ATM system does not accept any number greater than 2147483647 as the number&nbsp;of $20 bills on startup Function being tested:&nbsp;System accepts initial cash amount &nbsp;Initial state of the system:&nbsp; System is requesting the initial cash amount Steps to reproduce: 1. Enter a number&nbsp;greater than 2147483647 Expected outcome: System is on Actual outcome: A failure message saying &quot;Must be a valid integer &gt;= 0&quot;. Regression Test: Defect still exists in version 1.1 | Abhilash Paul | 2 | Doing | MFT; v1.0; v1.1
25 | Issue | System does not show any output or log entry to confirm a connection with Bank has been established | MFT System does not show any output or log entry to confirm a connection with Bank has been established Function being tested:&nbsp;Connection to the bank is established &nbsp;Initial state of the system:&nbsp; System has just been turned on Steps to reproduce: 1. Insert Card 1 and enter the PIn 42 2. Check the log for any entries that show a connection with the bank has been established Expected outcome: System output should demonstrate that a connection has been established to the Bank Actual outcome: No output or log entry&nbsp; found to confirm a connection to the bank is established Regression Test:Defect still exists in version 1.1 | Abhilash Paul | 2 | Doing | MFT; v1.0; v1.1
26 | Issue | $ sign is missing from withdraw amount list | MFT Function being tested: Missing $ sign from amount 60 when withdraw performed Initial state of the system:&nbsp; ATM is off. Steps to reproduce: Turn on the ATM and enter a valid number of bills. Click on insert card Type 2 and press enter Insert PIN 1234 Option 1 selected to Withdraw Option 1 selected to choose Checking Expected outcome: System should display amount with $ sign before the amount digit Actual outcome:All amounts has $ sign at the beginning of the amount except 60 | Bilal Ahmed | 2 | Doing | MFT; v1.1
27 | Issue | Only able to withdaw $20 from checking account | MFT Function being tested: System performs a legitimate withdrawal transaction properly Initial state of the system:&nbsp; ATM is off. Steps to reproduce: Turn on the ATM and enter a valid number of bills. Click on insert card Type 1 and press enter Insert PIN 42 Option 1 selected to Withdraw Opention 1 selected for Checking account Tried withdrawing $20, $40, $60 $100 Expected outcome: System dispenses this amount of cash; System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) Actual outcome:Only able to withdarw $20 with correct log but only once. | Bilal Ahmed | 2 | Doing | MFT; v1.1